## Start here
ALE quarterly component supply review
Template for reviewing approved repeat components, open supply risks, drawing changes, reorder timing and next quarter demand.
Use this file after a component has moved beyond first batch and is suitable for planned repeat supply.
Step | Action | Review standard
1 | Set the review period and customer details on the dashboard. | Cadence | Quarterly, or before a shutdown or production change.
2 | Update the Parts register with current demand, stock position, lead time, supplier status and required dates. | Scope | Approved repeat parts, critical spares, second-source parts and planned demand.
3 | Use Drawing inspection review to capture revision changes, inspection requirements and missing records. | Main output | One agreed action list for drawings, stock, orders, inspection and supply risk.
4 | Use Quality delivery review to record batch issues, late deliveries and inspection concerns from the quarter. | Not for | Random one-off quoting, design responsibility, or uncontrolled urgent work.
5 | Record decisions and actions in Action register before the meeting closes.
6 | Use the Quarterly review sheet as the meeting run sheet and customer-facing summary.
Contact ALE | www.alfredlewis.com.au

## Quarterly dashboard
Quarterly component supply review dashboard
Summary of next quarter demand, part risk, drawing status, open actions and reorder signals.
Review details |  |  | Live review indicators
Customer |  |  | Indicator | Value | Response
Review period |  |  | Parts due inside 30 days | 0 | Confirm PO timing and stock position.
Review date |  |  | Parts at reorder review | 2 | Check batch quantity and lead time.
ALE account owner |  |  | Single-source parts | 1 | Confirm second-source need or planned reserve.
Customer attendees |  |  | High or critical risk parts | 1 | Review drawings, inspection records and next action.
Next review due |  |  | Open drawing or inspection items | 2 | Close before the next production release.
|  |  | Overdue actions | 0 | Escalate owner and completion date.
|  |  | Open actions | 2 | Confirm owner and due date.
Quarterly decisions
Decision area | Current position | Agreed action | Owner | Due date | Notes
Demand
Orders
Drawings and revisions
Inspection records
Risk parts
Next quarter

## Parts register
Parts register
Quarterly view of repeat components, demand, stock position, lead time and supply risk.
Review item ID | Criticality | Equipment or line | Component or part family | Part description | Customer part number | ALE ref | Drawing number | Rev | Material and finish | Annual demand | Next 90 day demand | Usual batch qty | Stock on hand | Reorder point | Current supplier status | Lead time weeks | Last order date | Next required date | Supply status | Drawing and inspection status | Risk level | Owner | Next action | Target date | Notes
QCSR-001 | High | Packing line 2 | Roller shaft | Drive roller shaft | CUST-1001 | ALE-REF | DRG-001 | A | 316 stainless | 120 | 30 | 10 | 6 | 10 | Single source | 4 |  |  | Reorder review | Current | High | Maintenance | Confirm next batch timing
QCSR-002 | Medium | Pump skid | Gland housing | Seal gland housing | CUST-2004 | ALE-REF | DRG-057 | B | 4140, black oxide | 40 | 8 | 4 | 4 | 4 | Approved | 5 |  |  | Reorder review | Review required | Medium | Engineering | Check drawing revision
Formulas:
Supply status = IF(COUNTA([Criticality]:[Next required date])=0,"",IF(AND([Next required date]<>"",[Next required date]<TODAY()+30),"Due inside 30 days",IF(AND([Stock on hand]<>"",[Reorder point]<>"",[Stock on hand]<=[Reorder point]),"Reorder review",IF(OR([Current supplier status]="Single source",[Current supplier status]="Supplier concern"),"Supplier risk","Monitor"))))

## Quarterly review
Quarterly component supply review
Meeting run sheet for customer and ALE review of approved repeat component supply.
Review area | Prompt | Notes | Decision or action | Owner | Due date | Status | Reference | Follow-up
1. Demand and production outlook | Which parts are expected in the next 90 days?
2. Open and upcoming orders | Are purchase orders, required dates and batch quantities clear?
3. Critical spares and reorder triggers | Which parts are at, below or close to reorder point?
4. Drawing and revision control | Have any drawings, materials, finishes or revisions changed?
5. Inspection and quality records | Are any inspection records, certificates or approval packs missing?
6. Supplier risk and second-source need | Which parts are single source or exposed to lead time risk?
7. Pricing, batch size and commercial notes | Are batch sizes, pricing breaks or stocking arrangements still suitable?
8. Next quarter actions | What must be closed before the next review?

## Action register
Action register
Open decisions and follow-up actions from quarterly component supply reviews.
Action ID | Review date | Category | Action | Owner | Status | Priority | Timing | Due date | Notes
ACT-001 |  | Drawing | Confirm current drawing revision for roller shaft family. | Engineering | Open | High | No due date
ACT-002 |  | Ordering | Issue PO for next quarter pump housing batch. | Procurement | Open | Medium | No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
Formulas:
Timing = IF(COUNTA([Action]:[Due date])=0,"",IF([Status]="Closed","Closed",IF([Due date]="","No due date",IF([Due date]<TODAY(),"Overdue",IF([Due date]<=TODAY()+14,"Due inside 14 days","On track")))))

## Order forecast
Order forecast
Rolling 12-month view of expected demand, confirmed orders and parts at risk.
Month | Expected part families | Expected units | Confirmed PO units | At-risk part families | Required action | Owner | Status | Notes
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
2027-04-01
2027-05-01

## Drawing inspection review
Drawing and inspection review
Revision control, inspection requirements and missing records for repeat component supply.
Item ID | Part family | Part description | Customer part number | Drawing number | Current rev | Rev changed? | Material or finish changed? | Inspection evidence required | Last inspection record | Missing record | Action required | Status
DI-001 | Roller shafts | Drive roller shaft | CUST-1001 | DRG-001 | A | No | No | Dimensional report |  | No | Confirm next report format | Open
DI-002 | Pump housings | Seal gland housing | CUST-2004 | DRG-057 | B | Yes | No | FAIR and material cert |  | Yes | Confirm revision and inspection points | Open

## Quality delivery review
Quality and delivery review
Quarterly record of delivery performance, batch issues and inspection concerns.
Record ID | Part family | Customer part number | Order or batch | Due date | Delivered date | Qty | On time? | Inspection issue? | NCR or concern | Action required | Status
QD-001 | Roller shafts | CUST-1001 | PO/sample |  |  |  |  | No |  |  | Closed

## Commercial capacity notes
Commercial and capacity notes
Batch size, lead time, order timing and capacity notes for repeat supply planning.
Note ID | Part family | Current batch qty | Proposed batch qty | Price break or setup note | Lead time note | Capacity or reservation note | Customer decision | ALE action | Status
CC-001 | [8 empty] | Open

## Lists
Dropdown lists and field notes
Reference values used in the workbook.
Criticality | Supplier status | Risk level | Action status | Action category | Timing
Critical | Approved | Critical | Open | Demand | Overdue
High | Single source | High | In progress | Ordering | Due inside 14 days
Medium | Supplier concern | Medium | Closed | Drawing | On track
Low | Under review | Low | Deferred | Inspection | No due date
| No current supplier |  |  | Quality | Closed
Supplier risk
Commercial
Other