## Read me
ALE shutdown and outage supply planning template
Use this file to control machined spare parts, drawings, ordering, inspection, external operations, kitting and post-outage follow-up before a shutdown or outage.
Purpose | This template helps maintenance, engineering and procurement teams identify the machined components that can delay a shutdown if drawings, material, inspection, manufacture or dispatch are not ready.
Best use | Start 8 to 12 weeks before the outage for known repeat parts. Start earlier for castings, heat treatment, plating, coating, hard anodising, grinding, specialist material or first-time manufacture.
ALE pathway | Review the component. Check drawing and material readiness. Select the supply route. Confirm inspection requirements. Order early enough to protect the outage date.
Not for | Uncontrolled emergency buying after the plant is already down, unless drawings, material, inspection points and supply history are already understood.
Primary output | A controlled outage parts list showing what must be made, ordered, inspected, packed and on site before work starts.
Working tabs | Outage Overview, Parts Register, Ordering Plan, Drawing Inspection, Supplier Readiness, Kitting Dispatch, Risk and Escalation, Communication Log and Post-Outage Review.
Website use | This template can be offered from the ALE shutdown-outage supply planning page and linked to the Component Supply Review pathway.
File owner | Customer maintenance, engineering or procurement owner.
ALE contact | To be completed by ALE before issue.
Version | Template v1.0
Date | 2026-06-09
Notes | Do not upload uncontrolled customer drawings to public or shared systems. Keep drawing files, revision records and inspection data in the approved project folder.
Contact Us at | www.alfredlewis.com.au

## Outage Overview
Outage overview
Complete this before building the parts register. Dates drive ordering pressure, inspection cut-offs and escalation.
Customer |  | Site |  | Outage name | Prepared by | Date prepared | 46182.91
Primary contact |  | Role |  | Phone | Email | ALE contact
Outage start date |  | Outage finish date |  | Required parts on site by | Planning status | Revision | 1
Equipment or line
Outage scope
Known shutdown risk
Parts already identified |  | Parts still to review |  | Drawings missing | External operations required | Transport constraint
Ordering cut-off agreed |  | Inspection pack required |  | Site receiving rules confirmed | Kitting required | After-hours contact
Internal customer owner |  | Engineering owner |  | Procurement owner | Maintenance owner | Stores owner
ALE review required |  | Component supply review completed |  | First batch needed | Repeat supply candidate | Critical parts register candidate
General notes
Planning checkpoints | Owner | Due date | Status | Notes
Drawing pack complete |  |  | Not started
Material and finish confirmed |  |  | Not started
Critical parts selected |  |  | Not started
POs placed |  |  | Not started
Inspection requirements agreed |  |  | Not started
Parts packed and dispatched |  |  | Not started
Post-outage review booked |  |  | Not started

## Lists
Template lists
Controlled dropdown values used in this workbook.
Criticality | Supply status | Drawing status | Inspection status | Risk rating | Owner | Yes No | Manufacturing source
A - outage stop risk | Not started | Current | Not set | Low | Customer | Yes | ALE
B - outage delay risk | Info required | Needs revision | Features listed | Moderate | ALE | No | Current supplier
C - normal outage spare | Drawing review | Missing | Inspection plan agreed | High | External supplier | TBC | New supplier
Watch item | Quoted | Customer to confirm | First batch approved | Critical | Shared |  | Stock
| PO placed | Not required | Batch inspected |  |  |  | Customer supplied
| In manufacture |  | Closed |  |  |  | Other
External processing
Inspecting
Packed
Dispatched
Received
Closed

## Parts Register
Outage parts register
List every machined part, bought item and external operation that can affect outage completion.
Part ID | Part description | Equipment or line | Function in machine | Consequence if unavailable | Drawing rev | Material | Finish or external ops | Qty required | Qty on hand | Qty to order | Criticality | Manufacturing source | Supply status | Required on site | Latest order date | Lead time days | Readiness notes
EXAMPLE-001 | Drive shaft, stainless | Filling line 2 | Transfers drive to index unit | Line cannot recommission without part | Rev B | 316 stainless | Passivation | 2 | 0 | 2 | A - outage stop risk | ALE | Info required |  |  |  | Confirm drawing, material and key fits before order.
Formulas:
Lead time days = IF(OR([Part ID]="",[Latest order date]=""),"",[Latest order date]-TODAY())

## Dashboard
Outage supply dashboard
Summary of the register. Check this before every shutdown planning meeting.
Metric | Result | Target or trigger | Action | Status count | Count | Risk rating | Count
Total listed parts | 1 | All outage-affected parts listed | Check scope against maintenance plan | Not started | 0 | Low | 0
A-critical parts | 1 | No A-critical part without PO or drawing control | Escalate missing information | Info required | 1 | Moderate | 0
Qty still to order | 2 | All required spares covered before cut-off | Place or chase POs | Drawing review | 0 | High | 0
Open orders | 0 | Confirmed due date before site need date | Confirm dates | PO placed | 0 | Critical | 0
Drawing gaps | 0 | No missing critical drawings | Owner to resolve | In manufacture | 0
Items due in next 14 days | 0 | No unconfirmed part inside 14 days | Escalate | External processing | 0
High or critical risks | 0 | No open high or critical risks | Review risk actions | Inspecting | 0
Packed or dispatched | 0 | Confirm kitting before outage starts | Check dispatch log | Packed | 0
Received on site | 0 | Confirm goods receipt and storage location | Close supply loop | Dispatched | 0
Closed after outage | 0 | Move repeat items to critical parts register | Update post-outage review | Received | 0

## Ordering Plan
Ordering plan
Control orders, due dates, supplier confirmations and escalation before the outage window.
Part ID | Part description | Order type | Supplier | PO number | Issue date | Required date | Status | Confirmed date | Expedite date | Owner | Notes

## Drawing Inspection
Drawing and inspection control
Record the drawing, revision, critical features and inspection evidence needed before parts enter manufacture.
Part ID | Controlled drawing file | Revision | Date checked | Drawing status | Critical features | Inspection evidence required | Inspection status | Approval owner | Open issue | Notes

## Supplier Readiness
Supplier and external operations readiness
Track material supply, heat treatment, plating, coating, anodising, grinding, laser work and other outside operations.
Part ID | Operation or supply item | Supplier | Quote requested | Quote received | PO issued | Material or cert required | Due to supplier | Due back | Status | Escalation owner | Constraint | Notes

## Kitting Dispatch
Kitting and dispatch control
Group parts by equipment area and confirm packed, labelled, dispatched and received status before the outage starts.
Kit ID | Part ID | Equipment area | Qty packed | Pack date | Label or bin | Delivery method | Dispatch status | Dispatched date | Received by | Received date | Notes

## Risk and Escalation
Risk and escalation log
Use this tab for any part, drawing, supplier, inspection or transport issue that can affect the outage date.
Risk ID | Part ID | Risk | Cause | Consequence | Risk rating | Owner | Action | Due date | Status | Escalation trigger

## Communication Log
Communication and decision log
Record decisions, requests and owner actions. Use this when multiple teams are working against one outage date.
Date | Contact | Company | Topic | Decision or request | Owner | Due date | Status | Notes

## Post-Outage Review
Post-outage review
Capture what was used, what failed, what arrived late and what should move into a critical parts register.
Part ID | Part description | Used during outage | Fit issue | Quality issue | Delivery issue | Qty remaining | Reorder trigger | Move to critical parts register | Drawing update needed | Supplier issue | Action | Owner | Status