## Start here
ALE shutdown spares planning calendar
Working template for maintenance, procurement and operations teams preparing machined spares before a planned shutdown or outage.
Section | Instruction
Use this file to | Set dates, list parts, check drawing status, confirm inspection evidence, set order dates and track kit readiness before shutdown.
Best use | Start 8 to 12 weeks before the shutdown where repeat machined components, replacement parts or second-source risk may affect the maintenance window.
Not for | Uncontrolled emergency quoting, one-off hobby work, or parts without enough information to assess material, drawing and inspection requirements.
Primary next step | Start a component supply review: https://alfredlewis.com.au/component-supply-review/
Related customer programme | Shutdown and outage supply planning: https://alfredlewis.com.au/wp-content/uploads/2026/06/ALE_shutdown_outage_supply_planning_template.xlsx

## Overview
Shutdown overview
Enter the shutdown details once. Dates feed the planning calendar and order timing tabs.
Input | Detail | Planning status
Customer / site |  | Total parts listed | 4
Shutdown or outage name |  | High / critical risk parts | 3
Shutdown start date | 2026-09-01 | Order date due or missed | 0
Shutdown end date | 2026-09-07 | Drawing gaps | 3
Prepared by |  | Inspection evidence required | 3
Internal owner |  | Kits not ready | 3
Date prepared | 46183.1685
Primary machinery or line
Main supply risk
Notes

## Planning calendar
Shutdown planning calendar
Work back from the shutdown start date. Adjust owners and dates to suit the plant, lead time and supplier approval path.
Planning point | Target date | Owner | Status | Required action | Output / evidence | Escalation trigger
T - 12 weeks | 2026-06-09 |  | Not started | List planned maintenance work, affected equipment and likely machined spares. | Initial parts list | No parts list agreed
T - 10 weeks | 2026-06-23 |  | Not started | Check drawings, revisions, materials, finishes and known supplier history. | Drawing and data gap list | Missing drawings or old revisions
T - 8 weeks | 2026-07-07 |  | Not started | Confirm critical parts, current stock, minimum stock and lead time. | Critical spares list | Single-source parts or no current stock
T - 6 weeks | 2026-07-21 |  | Not started | Raise orders for long-lead machined parts and outsourced finishing. | Purchase orders issued | Target order date missed
T - 4 weeks | 2026-08-04 |  | Not started | Confirm machining status, inspection plan and certificates required. | Supplier readiness update | No confirmed delivery date
T - 2 weeks | 2026-08-18 |  | Not started | Confirm received parts, inspection evidence and kit allocation. | Kit readiness report | Parts not received or not inspected
T - 1 week | 2026-08-25 |  | Not started | Pack, label and stage parts by line, machine and work order. | Kitted spares ready | Kit incomplete
Shutdown week | 2026-09-01 |  | Not started | Track part usage, urgent changes and any non-conforming items. | Shutdown supply log | Unexpected part shortage
T + 1 week | 2026-09-14 |  | Not started | Record consumed parts, unused parts, failures and reorder actions. | Post-shutdown parts review | Critical part consumed without reorder
T + 2 weeks | 2026-09-21 |  | Not started | Update the critical parts register and set the next reorder triggers. | Updated register | Repeat part not added to register

## Parts calendar
Shutdown parts calendar
List every machined spare or repair part that could affect the shutdown window. Use the target order date to avoid last-week pressure.
Area / system | Equipment | Part name | Drawing / part number | Revision | Material / finish | Current stock | Critical qty | Required qty | Lead time weeks | Shutdown required date | Target order date | Supplier | Supplier status | Drawing status | Inspection evidence needed | Risk rating | Order status | Owner | Notes
Packaging line | Film handling | Pinch roller shaft |  |  | Stainless steel | 0 | 2 | 4 | 5 | 2026-08-25 | 2026-07-21 |  | To confirm | Needs review | Yes | High | Not started
Pump station | Transfer pump | Bearing housing |  |  | Cast iron / machined | 1 | 1 | 2 | 6 | 2026-08-25 | 2026-07-14 |  | To confirm | Needs review | Yes | High | Not started
Conveyor | Drive end | Drive shaft |  |  | 4140 / hardened | 0 | 1 | 1 | 7 | 2026-08-22 | 2026-07-04 |  | To confirm | Missing | Yes | Critical | Not started
General | Machine support | Spacer / collar set |  |  | Aluminium / anodised | 2 | 2 | 4 | 4 | 2026-08-25 | 2026-07-28 |  | To confirm | Current | No | Moderate | Not started
Formulas:
Target order date = IF([Shutdown required date]="","",[Shutdown required date]-([Lead time weeks]*7))

## Drawing and inspection
Drawing and inspection control
Use this tab to identify gaps before the part is ordered. Missing drawing data can stop the whole shutdown plan.
Part name | Drawing / part number | Revision | Drawing status | Critical features | Inspection method | Certificate / report required | Material certificate required | Owner | Close-out date | Notes
Pinch roller shaft |  |  | Needs review | Bearing journals, shaft shoulders, keyways | Micrometer, bore gauge, height gauge | Yes | Yes
Bearing housing |  |  | Needs review | Bores, faces, bolt pattern | CMM or FARO, bore gauge | Yes | If required
Drive shaft |  |  | Missing | Diameters, runout, keyways, threads | Centres, micrometer, runout check | Yes | Yes

## Supplier readiness
Supplier readiness
Track supplier status for machining, material, finishing, inspection and dispatch. Escalate gaps before the shutdown window closes.
Supplier / process | Part or package | PO status | Confirmed delivery date | Material status | Finishing status | Inspection status | Packing status | Risk | Owner | Next action | Notes
Machining supplier | Pinch roller shaft | Not issued |  | To confirm | Not required | Pending | Not packed | High |  | Issue RFQ with current drawing and required date
Finishing supplier | Anodised parts | Not issued |  | To confirm | Pending | Pending | Not packed | Moderate |  | Confirm finish specification and turnaround

## Kitting and dispatch
Kitting and dispatch
Once parts are received and inspected, kit them by machine, work order and shutdown task. Avoid loose spares arriving at the shutdown without allocation.
Kit ID | Area / line | Equipment | Work order | Part name | Qty required | Qty packed | Kit status | Location | Owner | Notes
KIT-001 | Packaging line | Film handling |  | Pinch roller shaft | 4 | 0 | Not started
KIT-002 | Pump station | Transfer pump |  | Bearing housing | 2 | 0 | Not started
KIT-003 | Conveyor | Drive end |  | Drive shaft | 1 | 0 | Not started

## Post shutdown review
Post-shutdown review
Record what was used, what failed, what was missing and what should move into the critical parts register.
Part name | Equipment | Used during shutdown | Issue found | Reorder required | Add to critical parts register | Drawing update needed | Inspection change needed | Owner | Due date | Notes
|  | No |  | No | No | No | No
|  | No |  | No | No | No | No

## Dropdown lists
Status | Risk | Drawing status | Inspection required | Supplier status | Order status | Kit status | Yes no
Not started | Low | Current | Yes | Approved | Not started | Not started | Yes
In progress | Moderate | Needs review | No | To confirm | RFQ sent | Part received | No
Waiting | High | Missing | If required | New supplier | Quoted | Inspection pending
Complete | Critical | Customer to confirm |  | Second-source required | Ordered | Ready
Blocked |  | Not required |  | Not required | In production | Blocked
Received
Blocked